## Dashboard
Lesson |  | Duration | ECO Domain & enabler
1. Business Environment | Topics | 9 Hrs
Day 1-2 | Foundation | 1-a | 3- BE 2- task .1- enabler
Day 3 | Strategic Alignment | 1-b | 3- BE 2- task .1- enabler
Day 3 | Project Benefits & Value | 1-c | Investigate that benefits are identified (3.2.1) Evaluate delivery options to deliver value (3.2.4), Assess opportunities to deliver value incrementally (2.1.1)
Day 4 | Organizational Culture and Change Management | 1-d | Assess organizational culture (3.4.1) Evaluate impact of organization change to project, and determine required actions (3.4.2) Evaluate impact of the project to the organization and determine required actions (3.4.3)
Day 4 | Project Governance | 1-e | Determine appropriate governance for a project (e.g., replicate organization governance) (2.14.1) Define escalation paths and thresholds (2.14.2)
Day 5 | Project Compliance | 1-f | 3.1.1,3.1.2,3.1.5
2. Start the Project |  | 8 hrs | 7-8 Hours
Day 5- 6 | Identify and Engage Stakeholders | 2-a | 1.9.1,2.4.1,2.4.2,2.4.4,2.2.1,2.2.2
Day 6- 7 | Form the Team | 2-b | 1.4.1,2.16.1,2.16.2,1.11.1,1.11.2
Day 8 | Build Shared Understanding | 2-c | 1.2.1,1.8.1,1.8.2,1.8.5,1.8.4,1.10.2,1.10.3,1.12.1,1.12.2
Day 8-9 | Determine Project Approach | 2-d | 2.13.1,2.13.2,2.13.3
3. Plan the Project |  | 12 Hrs | 12 Hrs
Day 10 | Planning Projects | 3-a
Day 10-11 | Scope | 3-b | 2.1.3,2.8.1,2.8.2,2.17.1
Day 12-13 | Schedule | 3-c | 2.6.1,2.6.2,2.6.3
Day 13-14 | Resources & Procurement | 3-d | 1.6.2,2.11.1,2.11.2,2.11.3,2.11.4,2.11.5
Day 14-15 | Budget | 3-e | 2.3.1,2.3.2,3.1.6,3.1.3
Day 16 | Risks | 3-f | 2.3.1,2.3.2,3.1.6,3.1.3
Day 16-17 | Quality | 3-g | 2.7.1,3.1.4,3.1.7
Day 17 | Integrate Plans | 3-h | 2.9.1,2.9.2,2.9.3,2.9.4,2.9.5,2.10.2
4. Lead the Project Team |  | 3 Hrs | 3-4 Hours
Day 17-18 | Craft your Leadership Style | 4-a | 1.2.3 , 1.2.4, 1.2.7, 1.11.3
| Create a Collaborative Project Team Environment | 4-b | 2.12.1, 2.12.2
| Empower the Team | 4-c | 1.2.2,1.2.5,1.4.4
| Support Team Member Performance | 4-d | 1.3.1, 1.3.2, 1.3.3, 1.3.4
| Communicate and Collaborate with Stakeholders | 4-e | 2.2.3,2.2.4,1.2.6,2.4.3,1.9.2,1.9.3,3.2.5
| Training, Coaching and Mentoring | 4-f | 1.6.1,1.5.1,1.5.2,1.5.3,1.5.4,1.13.1,1.13.2
| Manage Conflict | 4-g | 1.1.1,1.1.2,1.1.3,1.12.3,1.10.4,1.10.1
5 .Support Team Performance |  | 4 Hrs | 4 Hours
Day 19-20 | Implement Ongoing Improvements | 5-a
| Support Performance | 5-b | 2.2.3,2.2.4,1.4.2,1.4.3,1.6.3,1.6.4,1.11.4,2.12.3,2.13.4
| Evaluate Project Progress | 5-c | 2.8.3,1.6.4,2.6.5,2.6.6,2.5.3,2.1.2,2.7.2,2.7.3
| Manage Issues and Impediments | 5-d | 2.15.1,2.15.2,2.15.3,1.7.1,1.7.2,1.7.3,1.7.4
| Manage Changes | 5-e | 3.3.1,3.3.2,3.3.3,3.3.4,2.10.1,2.10.3,2.10.4
6. Close the Project / Phase |  | 1 Hour | 1 Hour
Day 20 | Project / Phase Closure | 5-a | 1.8.3,2.17.2,2.17.3
| Benefits Realization | 5-b | 3.2.2,3.2.3
| Knowledge Transfer | 5-c | 2.16.3
PMP Application

## agenda day1
Goal- Obtain our PMP
Today’s session is primarily to set the foundation:
Understand how the course will run
Get familiar with the PMP exam structure
Simplilearn LMS & PMI website walkthrough
Discuss our study plan and expectations
Clarify doubts and help you feel confident and ready
Chapter 1 - Foundation
| PMI website | Simplilearn Website
Team Charter | pmi.org | lms.simplilearn.com
domain neutral example
Be respectful t everyone | Digital KIT- PMI Deck ( need to claim digital key thru simplilearn LMS) | class recordings ( under Live classes) also session material
Everyone on time | 6 chapters pdf ( slides) ( same as trainer's deck) | assessment test ( Mock test from Simplilearn/ PMI
10min at the last -Q&A | chapter wise questions ( mastery builder PDF) | self learning videos
active listener | case study ( Shwape Lifestyle Centre) | 35 PDU certificate ( can be downloaded after completing course with 80 % attendance & 2 assessment cleared from assessment test
Operations/ Logistic querries - raise support ticket through LMS ( simplilearn) | spotlight videos
glossary ( definitions of PM Terminology)
Recommended books | Student work book
1. PMP Exam Content Outline ( MUST)
2. PMBOK 7th ed | PMP application
3. PROCESS/PRACTICE GUIDE
4. AGILE GUIDE RECOMENDED ( FOR PARTICIPANTS NOT EXPERIENCED IN AGILE )
5. PMI CODE OF ETHICS ( MUST)
555 usd member 129 usd + 405 usd
PMBOK 8th ed - jan 2026
ECO/ April 2026
100-120 hrs
5 mock test / review - 75%

## study plan
4 week Study Plan for PMP Date & timing need to filled by participant as per their availability)
Day | Hours | Mode | Details | Calendar Date | Timing | Status
Day 1 | 2 hrs | task revision | Chapter 1
Day 2 | 2 hrs | task revision | Chapter 2
Day 3 | 2 hrs | task revision + Scope questions | Chapter3 - Scope
Day 4 | 2 hrs | task revision + questions | Chapter 3-Schedule
Day 5 | 2 hrs | task revision + question | Chapter 3 - resource , procurement , cost
Day 6 | 2 hrs | task revision + question | Chapter 3 Quality & INtegration
Day 7 | 2 hrs | task revision + question | Chapter 4
Day 8 | 2 hrs | task revision + question | Chapter 4
Day 9 | 2 hrs | task revision + question | CHapter5
Day 10 | 2 hrs | task revision + question | Chapter5
Day 11 | 2 hrs | task revision + question | Chapter 6
Day 12 | 4 hrs | 500 questions practice | ( PMP assessmentpdf on drive)
Day 13 | 4 hrs | 500 questions practice | Continue with same
Day 14-16 | 4 hrs | MOCK TEST | Simplilearn mock Test + review exam
Day 17 | 4 hrs | MOCK TEST | Simplilearn mock Test + review exam
Day 18 | 4 hrs | MOCK TEST | Simplilearn mock Test + review exam
Day 19 | 4 hrs | MOCK TEST | Simplilearn mock Test + review exam
Day 20 | 4 hrs | MOCK TEST | Simplilearn mock Test + review exam
Day 21 | 4 hrs | PMI test -1 | LMS- PMI Test
Day 22 | 4 hrs | PMI Test 2-3 | LMS- PMI Test
Day 23 | 4 hrs | PMI test 3-4 | LMS- PMI Test
If score is not improving after 3rd mock etst Pls read PMBOK 7th Edition, Process guide & Agile practice guide
PMBOK 7th edition - 8 Hours
Process Guide - 8 Hours
Agile Practice guide- 4 Hours

## EVM in predictive
BCWS TILL DATA DATE | PV | PLANNED VALUE
BCWP TILL DATA DATE | EV | EARNED VALUE
| AC | ACTUAL COST
| SV | SCHEDULE VARIANCE
| SPI | SCHEDULE PERFORMANCE INDEX
| CV | CV COST VARIANCE
| CPI | CPI COST PERFORMANCE INDEX
FORECASTING | BAC | BUDGET AT COMPLETION
| EAC | ESTIMATE AT COMPLETION COST
| VAC | VARIANCE AT COMPLETION
| TCPI | TO COMPLETE PERFORMANCE INDEX

## evm in agile
AGILE
SPI | SP DELIVERED/SP PLANNED
CPI | PLANNED COST OF STORY POINT DELIVERED/ACTUAL COST INCURRED

## pdm relationship
PDM
1 | FS | FINISH TO START | SUCCESSOR CANNOT START UNTIL PRDECESSOR FINISHES
2 | SS | START TO START | SUCCESSOR CANNOT START UNTIL PREDECESSOR HAS STARTED
3 | FF | FINISH TO FINISH | SUCCESSOR CANNOT FINISH UNTIL PRED HAS FINISHED
4 | SF | START TO FINISH | SUCCESSOR CANNOT FINISH UNTIL PRED STARTS | TESTING
DOCUMENTATION

## cpm
|  |  | ES |  | Ef | ES |  | EF
|  |  |  | 4D |  |  | 3D
|  |  |  | Activity B |  |  | Activity D
ES |  | EF
| 3D |  | LS |  | LF | LS |  | LF | ES |  | EF
| Avctivity A | [8 empty] | 3D
[10 empty] | Activity F |  | FINISH
LS |  | LF | ES |  | EF | ES |  | EF
|  |  |  | 5D |  |  | 5D | `13 | LS |  | LF
|  |  |  | Activity C |  |  | Activity E
|  |  | LS |  | LF | LS |  | LF

## cost est in pred
ID | Activity | Resource | Average Rate ($/hr) | Tot Dur ( hrs) | Est cost | Activity ID | Activity Name | Duration (days) | Resources | Estimated Cost
1 | System Design | Solution Architect, | 80 | 40 | 3200 | A1 | Clear site and set up | 10 | Labor, Equipment | 300000
2 | UI/UX Design | UI/UX Designer | 60 | 40 | 2400 | A2 | Lay foundation | 20 | Labor, Materials, Equipment | 200000
3 | Backend Development | Backend Developer | 70 | 60 | 4200 | A3 | Build structural framework | 30 | Labor, Materials, Equipment | 300000
4 | Frontend Development | Frontend Developer | 65 | 40 | 2600 | A4 | Install roofing | 15 | Labor, Materials | 150000
5 | API Integration | API Developer | 70 | 24 | 1680 | A5 | Construct exterior walls | 25 | Labor, Materials | 250000
6 | Database Design | Database Administrator | 75 | 48 | 3600 | A6 | Construct interior walls | 20 | Labor, Materials | 200000
7 | Testing and QA | QA Engineer | 55 | 24 | 1320 | A7 | Install plumbing systems | 15 | Labor, Materials, Equipment | 150000
8 | DevOps Setup | DevOps Engineer | 80 | 40 | 3200 | A8 | Install electrical systems | 20 | Labor, Materials, Equipment | 200000
9 | Security Assessment | Security Analyst | 85 | 12 | 1020 | A9 | Install flooring | 10 | Labor, Materials | 100000
10 | Deployment | Release Manager | 70 | 12 | 840 | A10 | Paint walls | 10 | Labor, Materials | 100000
11 | User Training | Training Specialist | 50 | 40 | 2000
12 | Maintenance and Support | Support Engineer | 45 | 40 | 1800
[9 empty] | EST COST | Cum cost
[8 empty] | W1 | 30000 | 30000
| EST COST | Cum cost | [5 empty] | W2 | 42000 | 72000
W1 | 4000 | 4000 | [5 empty] | W3 | 50000 | 122000
W2 | 4200 | 8200 | [5 empty] | W4 | 50000 | 172000
W3 | 4000 | 12200 | [5 empty] | W5 | 55000 | 227000
W4 | 5000 | 17200 | [5 empty] | W6 | 30000 | 257000
W5 | 5500 | 22700 | [5 empty] | W7 | 43000 | 300000
W6 | 3000 | 25700 | [5 empty] | W8 | 60000 | 360000
W7 | 4300 | 30000 | [5 empty] | W9 | 40000 | 400000
W8 | 6000 | 36000 | [5 empty] | W10 | 60000 | 460000
W9 | 4000 | 40000 | [5 empty] | W11 | 65000 | 525000
W10 | 6000 | 46000 | [5 empty] | W12 | 70000 | 595000
W11 | 4000 | 51000 | [5 empty] | W13 | 80000 | 675000
W12 | 3000 | 56500 | [5 empty] | W14 | 70000 | 745000
W13 | 2000 | 59500 | [5 empty] | W15 | 65000 | 810000
W14 | 2000 | 61500 | [5 empty] | W16 | 60000 | 870000
[8 empty] | W17 | 50000 | 920000
[8 empty] | W18 | 45000 | 965000
[8 empty] | W19 | 30000 | 995000
[8 empty] | W20 | 20000 | 1015000

## comparison between contract typ
Criteria | Fixed Price | Cost Reimbursable | Time & Material (T&M)
Scope Clarity | High – well-defined upfront | Medium – may evolve during execution | Low – flexible and evolving
Cost Predictability | High – fixed total cost | Low – actual costs reimbursed | Low – based on actual time and materials
Buyer Risk | Low – cost is fixed | High – bears cost overruns | High – cost can increase with time
Seller Risk | High – must deliver within budget | Low – reimbursed for actual costs | Low – paid for actual work and materials |  | 200k
Flexibility | Low – changes require contract updates | Medium – scope can be adjusted | High – easy to adapt to changes | graduated t &M
Best Use Case | Well-defined deliverables and timelines | Research, innovation, or uncertain scope | Consulting, support, or evolving requirements
Example | $10,000 for a complete app | Reimbursement for R&D expenses + fee | $50/hour for developer + material costs

## COMP SCOPE
| Predictive (Waterfall) | Adaptive (Agile)
Scope Definition | Defined upfront | Evolving over time
Documentation | Detailed Scope Statement | Lightweight (Epics, User Stories)
Scope Baseline | Fixed | No fixed baseline
Change Control | Formal Change Requests | Incorporated into backlog updates
Key Artifact | WBS (Work Breakdown Structure) | Product Backlog
Planning Process | Scope > Time > Cost | Repeated at every iteration (Sprint)
Customer Role | Informed | Highly involved & collaborative

## pdm
1 | FS | FINISH START | SUCCESSOR TASK CAN ONLY START ONCE PREDECESSOR HAS FINISHED
|  | eg | LIGHT FIXTURES CAN ONLY START ONCE YOUR ELEC WIRING IS DONE
PAINTING CAN START ONLY ONCE PLASTER IS OVER
2 | SS | START TO START | SUCCESSOR CAN ONLY START ONCE PREDECESSOR HAS STARTED
|  | eg | SMOKE TESTING CAN START ONCE DEPLOYMENT HAS STARTED
REQ PRIORITISATION CAN ONLY START ONCE REQ COLLECTION HAS STARTED
3 | FF | FINISH TO FINISH | SUCCESSOR CAN ONLY FINISH ONCE PREDECESSOR HAS FINISHED
|  | eg | FINAL REPORT CAN ONLY FINISH ONCE PROOF READING DONE
FINAL DOCUMENTATION CAN FINISH ONCE TESTING CONCLUDES
FINAL REPORT COMPLETION ONCE OUR INSPECTION IS OVER
4 | SF | START TO FINISH | SUCCESSOR CAN ONLY FINISH ONCE PREDCESSOR HAS STARTED
|  | eg | OLD SERVER WILL CONTINUE UNTIL NEW SERVER IS INSTALLED
PROCURING OF PIPES WILL ONLY FINISH ONCE SELF MANUFACTURING STARTED
outsourcing pipes rcc
fs

## Scope in adaptive
|  | LEMON | ORANGE, APPLE
|  | S | M
S, M, L, XL, XXL
food delivery app
Vision statement | To revolutionize the food delivery experience by seamlessly connecting customers with their favorite restaurants and home chefs. Our platform ensures fast, reliable, and personalized service, empowering users to enjoy delicious meals anytime, anywhere, while supporting local businesses and promoting sustainability.
|  | size | sp | release |  | Release Backlog |  | Iteration/Sprint Backlog
Product Backlog | User authentication system. | S | 3 |  | R1 | User authentication system.
| Search functionality for restaurants and dishes. | M | 5 | r1 |  | Search functionality for restaurants and dishes. | Sprint 1 | As a customer, I want to search for restaurants by name so that I can quickly find my favorite places.
| Real-time GPS tracking for deliveries. | L | 8 | epics/feature/ user stories |  | Push notifications for order status updates. |  | As a customer, I want to filter search results by cuisine so that I can discover new dishes I like.
| Push notifications for order status updates. | S | 3 |  |  | Multiple payment methods. |  | As an administrator, I want the search algorithm to prioritize restaurants with higher ratings so that customers get better recommendations.
| Multiple payment methods (credit card, wallet, cash on delivery). | L | 8 |  | R2
| Integration with customer review and rating systems. | M | 5 |  |  | Integration with customer review and rating systems. |  | user story
| Bug fix Resolve issues with app crashes on older devices | M | 5 |  |  | Bug fix Resolve issues with app crashes on older devices |  | As a user What ( functionality) I get this value
| Restaurant and Chef Profiles | S | 3 |  |  | Restaurant and Chef Profiles
| Order History | M | 5 |  |  | Order History
| Favorites and Wishlists | M | 5 | r2 |  | Favorites and Wishlists
| Customer Feedback System | S | 3 |  |  | Customer Feedback System
| Promotions and Discounts | S | 3 |  | R3 | Promotions and Discounts
| Loyalty Program | S | 3 |  |  | Loyalty Program
| Multi-language Support | M | 5 |  |  | Multi-language Support
| Delivery Driver Tracking | M | 5 |  |  | Delivery Driver Tracking
| Contactless Delivery Option | L | 8 |  |  | Contactless Delivery Option
| Customizable Orders | M | 5 |  |  | Customizable Orders
| Live Customer Support Chat | M | 5 |  |  | Live Customer Support Chat
| Order Cancellation | S | 3 |  |  | Order Cancellation
| Heat Map for Popular Restaurants | L | 8 |  | R4 | Heat Map for Popular Restaurants
| Predictive Search Suggestions | S | 3 |  |  | Predictive Search Suggestions
| Dynamic Delivery Fee Calculation | M | 5 |  |  | Dynamic Delivery Fee Calculation
| Carbon Footprint Tracking | M | 8 |  |  | Carbon Footprint Tracking
114
|  | PERFORMANCE | 1 SPRINT 4 WEEKS ( 25 sp)